## Sheet1
Tasks should include how many TC's executed, defects logged, no. of automation scripts delivered, technical contributions to the team, etc.
Tasks (2/8-2/12) | Expected ETA | Actual ETA | Issues
Automation P1 - 2/12 - 5TC | 2016-02-12 | 2016-02-17 | Kraken14 being down, couldn’t verify script in a timely manner.
Tempest run on Kraken14 |  | 2016-02-11
Compare Rally/Tempest/SVT test cases | 2016-02-09 | 2016-02-08
Tempest cleanup script |  | 2016-02-10
Debug tempest failure logs |  | 2016-02-10
Tasks (2/15-2/19) | Expected ETA | Actual ETA | Issues
Automation P1 - 2/22 - 9TC | 2016-02-22 | 2016-02-19
Obtain/script opestack component versions - Kraken14 | 2016-02-13 | 2016-02-14 | Didn't know comands to obtain correct version. Had to ask Mane to help. This has been scripted into a bash script and placed in the root folder of kraken14
Kraken stage testing